## Plan
Plan ID | Plan name | Date of export
8xm1ft6lfkWna-pEJoDv6ckACbR6 | Water Quality Monitoring and Pool Maintenance System | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
X2nsQ6fIYkGS_NeFi7nN9ckAO3rG | Identify crowd-density research problem and scope | Planning |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-02-09 | 2026-02-02 |  | false | 2026-10-14 | SAAJITH M H M it22156310
ifIk4orGFEmQrKyPDdDuZMkAL7YZ | Identify drowning-detection research problem and scope | Planning |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-02-09 | 2026-02-02 |  | false | 2026-10-14 | SAAJITH M H M it22156310
NXqqi-LKX06hp68tgpZgcMkADIo1 | Identify water-quality research problem and scope | Planning |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-02-09 | 2026-02-02 |  | false | 2026-10-14 | NILOGINI Y it22247254
WbvpDsIsqUGo7nS2p8LFTMkAOefR | Select sensors and prepare bill of materials | Planning |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-03-20 | 2026-03-12 |  | false | 2026-10-14 | NILOGINI Y it22247254
f1RaofgYjkqDH5vLtlaWd8kAHumq | Identify garbage-intrusion research problem and scope | Planning |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-02-09 | 2026-02-02 |  | false | 2026-10-14 | ARSALAN M. Y.S. it22277336
UBoFUSjQEk-juXpPnwqAy8kAATcY | Literature review: crowd counting and bather load | Research |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-02-22 | 2026-02-05 |  | false | 2026-10-14 | SAAJITH M H M it22156310 |  |  | Pink
XUWctry7aEuaBwmjb92SAMkAPoTf | Collect and clean swimmer datasets (Roboflow) | Research |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-03-31 | 2026-03-15 |  | false | 2026-10-14 | SAAJITH M H M it22156310
QSPeuiD1Nk6UEsu2x0mqg8kACvZv | Literature review: IoT water monitoring and pool standards | Research |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-02-22 | 2026-02-05 |  | false | 2026-10-14 | NILOGINI Y it22247254 |  |  | Pink
SpSYrgweVkCfI0uhbUGhMMkAG2sT | Literature review: drowning behaviour and detection systems | Research |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-02-24 | 2026-02-05 |  | false | 2026-10-14 | SAAJITH M H M it22156310
YVK86cnj4E6UBHGZrk9FdskAORQB | Collect and clean drowning dataset (3 classes) | Research |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-04-05 | 2026-03-12 |  | false | 2026-10-14 | SAAJITH M H M it22156310
6FmOE0Ksxk-gdMsa9BKMk8kABkWQ | Literature review: litter detection and pose estimation | Research |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-02-22 | 2026-02-05 |  | false | 2026-10-14 | SAAJITH M H M it22156310
kmOIILTvokex37MQs_AEp8kAGZot | Collect and annotate pool garbage dataset | Research |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-04-02 | 2026-03-12 |  | false | 2026-10-14 | SAAJITH M H M it22156310 |  |  | Pink
D6W8AIxlR0aPMBPOQHgCzckAJTYc | Train and compare YOLOv8 swimmer detectors v1 vs v2 | Development |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-05-06 | 2026-04-08 |  | false | 2026-10-14 | SAAJITH M H M it22156310
C5W3hVkAMU2anXNy2pXgA8kAMcWz | Implement pool-region filter and count smoothing | Development |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-05-24 | 2026-05-12 |  | false | 2026-10-14 | SAAJITH M H M it22156310
I2tk6KVhdUWojjEoUcgquckALK_i | Implement bather-load scheduler and capacity model | Development |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-06-12 | 2026-05-22 |  | false | 2026-10-14 | SAAJITH M H M it22156310
WQpCGknVUkm8gXCXl-sRkskAGEWQ | Build shared backend and central decision engine | Development |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-07-28 | 2026-07-01 |  | false | 2026-10-14 | SAAJITH M H M it22156310
nlN-GJfsXEWRgplciwk3z8kAGNXM | Build unified dashboard and PDF session report | Development |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-08-15 | 2026-07-25 |  | false | 2026-10-14 | SAAJITH M H M it22156310
6gVs2je_qE-C3O4yvZfwWskAKq7U | Build Wokwi + ESP32 prototype with ThingSpeak | Development |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-04-05 | 2026-03-18 |  | false | 2026-10-14 | SAAJITH M H M it22156310
YWE-wf47ykKKSul16OqtlckAHPNf | Prepare dataset and train Random Forest classifier | Development |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-04-25 | 2026-04-01 |  | false | 2026-10-14 | NILOGINI Y it22247254
sn8mxyeIYUG8pq4zyiUSzMkAAZPj | Assemble Arduino sensor node (pH, turbidity, TDS, temp) | Development |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-05-15 | 2026-05-01 |  | false | 2026-10-14 | NILOGINI Y it22247254
YH5TauUGJUG-fsV-Yl1Mt8kANSNt | Implement sensor calibration stored in EEPROM | Development |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-06-02 | 2026-05-20 |  | false | 2026-10-14 | NILOGINI Y it22247254
chtmR_fkyEG01pxvpVhHVskAFah2 | Retrain with XGBoost and stratified split | Development |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-07-12 | 2026-07-01 |  | false | 2026-10-14 | NILOGINI Y it22247254
lZ92ZHSfRkyVWz0tkQZypMkADAIM | Train baseline YOLOv8 model on Kaggle GPU | Development |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-04-25 | 2026-04-08 |  | false | 2026-10-14 | SAAJITH M H M it22156310
jdrL_EqdyEGffL62KU-DbckAJ5-B | Fine-tune YOLOv8s for 100 epochs | Development |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-05-15 | 2026-05-01 |  | false | 2026-10-14 | SAAJITH M H M it22156310
T3tn3LazIUeO519Scs_ZvckABCEQ | Implement live detection with phone camera | Development |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-06-01 | 2026-05-20 |  | false | 2026-10-14 | SAAJITH M H M it22156310
LjDcn7gM1E2DZNKpGqwQLckAPoG8 | Implement 3-frame alert confirmation and SAFE/DANGER | Development |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-06-12 | 2026-06-01 |  | false | 2026-10-14 | SAAJITH M H M it22156310
UtgjbMd3E02HBrfic3GEgskAP1f3 | Implement Flask-SocketIO real-time alerts | Development |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-07-12 | 2026-07-01 |  | false | 2026-10-14 | SAAJITH M H M it22156310
xOTZ1VsG9Eyet6dZ-Ph7hskAPNBr | Train YOLOv8n garbage model in Colab | Development |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-04-25 | 2026-04-10 |  | false | 2026-10-14 | SAAJITH M H M it22156310
qkrvcBXPtUyxsqg_4JtxVskADLVJ | Implement MongoDB logging and pose-based intent (v1) | Development |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-06-15 | 2026-05-15 |  | false | 2026-10-14 | SAAJITH M H M it22156310
GsRAYHcUbEeKYPjbWri5o8kAJ9QQ | Redesign for live camera with object tracking (v2) | Development |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-10-08 | 2026-10-01 |  | false | 2026-10-14 | SAAJITH M H M it22156310
DaU1ZZsuxEuYI7EVDGIyqMkAIHkU | Implement throw vs accidental intent rules (v2) | Development |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-10-10 | 2026-10-05 |  | false | 2026-10-14 | SAAJITH M H M it22156310
ohCFx7AkAE6aEMAsvpHwsMkAItK3 | Implement sinking-garbage and pool-floor detection | Development |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-10-12 | 2026-10-07 |  | false | 2026-10-14 | SAAJITH M H M it22156310
XDoyU_DiQEaIZIveXuiN1skAA8Li | Record throw clips and retrain model (v2 notebook) | Development |  | Not started | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-10-22 | 2026-10-14 |  | false
uruv5qv470qtHFN741gqMskAEKdX | Integration testing (27 automated system checks) | Testing & Integration |  | Completed | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-09-05 | 2026-08-15 |  | false | 2026-10-14 | SAAJITH M H M it22156310
aXhFiPPYskG89GPspoFYwckAOOLD | Integrate water card into dashboard and test sensors | Testing & Integration |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-09-05 | 2026-08-15 |  | false | 2026-10-14 | NILOGINI Y it22247254
d89TgB5ODUqw4mfUhfs7TckAKhrB | Integrate drowning module into dashboard and test | Testing & Integration |  | Completed | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-08-15 | 2026-07-20 |  | false | 2026-10-14 | SAAJITH M H M it22156310
aASwIWEJXkSJjJtCuwDeX8kAOZSg | Integrate garbage module into unified dashboard | Testing & Integration |  | Completed | Medium | ARSALAN M. Y.S. it22277336 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-07-20 | 2026-07-01 |  | false | 2026-10-14 | SAAJITH M H M it22156310
3LM-IhnmZ0-3SJ4hrQZc7MkANjab | Write individual and group final thesis | Documentation |  | Not started | Medium | SAAJITH M H M it22156310 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-10-22 | 2026-09-25 |  | false
EIAe8TJQ8ESdomsZzcVH4ckAKmRg | Write individual final thesis (Component 2) | Documentation |  | Completed | Medium | NILOGINI Y it22247254 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-10-20 | 2026-09-25 |  | false | 2026-10-14 | NILOGINI Y it22247254
ArWdWDhaFE-d9vlCtzFkl8kAC1LT | Write individual final thesis (Component 3) | Documentation |  | Not started | Medium | SHAFAN N M it22248480 | SAAJITH M H M it22156310 | 2026-10-14 | 2026-10-20 | 2026-09-25 |  | false

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
X2nsQ6fIYkGS_NeFi7nN9ckAO3rG | Identify crowd-density research problem and scope | ONxyLl54k0mTc_lJ2n9c_8kAPr_3 |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-02-09 | 2026-02-02 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
ifIk4orGFEmQrKyPDdDuZMkAL7YZ | Identify drowning-detection research problem and scope | ONxyLl54k0mTc_lJ2n9c_8kAPr_3 |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-02-09 | 2026-02-02 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
NXqqi-LKX06hp68tgpZgcMkADIo1 | Identify water-quality research problem and scope | ONxyLl54k0mTc_lJ2n9c_8kAPr_3 |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-02-09 | 2026-02-02 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411
WbvpDsIsqUGo7nS2p8LFTMkAOefR | Select sensors and prepare bill of materials | ONxyLl54k0mTc_lJ2n9c_8kAPr_3 |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-03-20 | 2026-03-12 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411
f1RaofgYjkqDH5vLtlaWd8kAHumq | Identify garbage-intrusion research problem and scope | ONxyLl54k0mTc_lJ2n9c_8kAPr_3 |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-02-09 | 2026-02-02 |  | false | 2026-10-14 | 7d4d2156-a035-4149-9b74-1569eec88cfa
UBoFUSjQEk-juXpPnwqAy8kAATcY | Literature review: crowd counting and bather load | b-So2S7d70yp2V2sRjkJkMkAHhOk |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-02-22 | 2026-02-05 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd |  |  | Pink
XUWctry7aEuaBwmjb92SAMkAPoTf | Collect and clean swimmer datasets (Roboflow) | b-So2S7d70yp2V2sRjkJkMkAHhOk |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-03-31 | 2026-03-15 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
QSPeuiD1Nk6UEsu2x0mqg8kACvZv | Literature review: IoT water monitoring and pool standards | b-So2S7d70yp2V2sRjkJkMkAHhOk |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-02-22 | 2026-02-05 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411 |  |  | Pink
SpSYrgweVkCfI0uhbUGhMMkAG2sT | Literature review: drowning behaviour and detection systems | b-So2S7d70yp2V2sRjkJkMkAHhOk |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-02-24 | 2026-02-05 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
YVK86cnj4E6UBHGZrk9FdskAORQB | Collect and clean drowning dataset (3 classes) | b-So2S7d70yp2V2sRjkJkMkAHhOk |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-04-05 | 2026-03-12 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
6FmOE0Ksxk-gdMsa9BKMk8kABkWQ | Literature review: litter detection and pose estimation | b-So2S7d70yp2V2sRjkJkMkAHhOk |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-02-22 | 2026-02-05 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
kmOIILTvokex37MQs_AEp8kAGZot | Collect and annotate pool garbage dataset | b-So2S7d70yp2V2sRjkJkMkAHhOk |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-04-02 | 2026-03-12 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd |  |  | Pink
D6W8AIxlR0aPMBPOQHgCzckAJTYc | Train and compare YOLOv8 swimmer detectors v1 vs v2 | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-05-06 | 2026-04-08 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
C5W3hVkAMU2anXNy2pXgA8kAMcWz | Implement pool-region filter and count smoothing | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-05-24 | 2026-05-12 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
I2tk6KVhdUWojjEoUcgquckALK_i | Implement bather-load scheduler and capacity model | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-06-12 | 2026-05-22 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
WQpCGknVUkm8gXCXl-sRkskAGEWQ | Build shared backend and central decision engine | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-07-28 | 2026-07-01 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
nlN-GJfsXEWRgplciwk3z8kAGNXM | Build unified dashboard and PDF session report | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-08-15 | 2026-07-25 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
6gVs2je_qE-C3O4yvZfwWskAKq7U | Build Wokwi + ESP32 prototype with ThingSpeak | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-04-05 | 2026-03-18 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
YWE-wf47ykKKSul16OqtlckAHPNf | Prepare dataset and train Random Forest classifier | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-04-25 | 2026-04-01 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411
sn8mxyeIYUG8pq4zyiUSzMkAAZPj | Assemble Arduino sensor node (pH, turbidity, TDS, temp) | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-05-15 | 2026-05-01 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411
YH5TauUGJUG-fsV-Yl1Mt8kANSNt | Implement sensor calibration stored in EEPROM | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-06-02 | 2026-05-20 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411
chtmR_fkyEG01pxvpVhHVskAFah2 | Retrain with XGBoost and stratified split | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-07-12 | 2026-07-01 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411
lZ92ZHSfRkyVWz0tkQZypMkADAIM | Train baseline YOLOv8 model on Kaggle GPU | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-04-25 | 2026-04-08 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
jdrL_EqdyEGffL62KU-DbckAJ5-B | Fine-tune YOLOv8s for 100 epochs | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-05-15 | 2026-05-01 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
T3tn3LazIUeO519Scs_ZvckABCEQ | Implement live detection with phone camera | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-06-01 | 2026-05-20 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
LjDcn7gM1E2DZNKpGqwQLckAPoG8 | Implement 3-frame alert confirmation and SAFE/DANGER | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-06-12 | 2026-06-01 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
UtgjbMd3E02HBrfic3GEgskAP1f3 | Implement Flask-SocketIO real-time alerts | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-07-12 | 2026-07-01 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
xOTZ1VsG9Eyet6dZ-Ph7hskAPNBr | Train YOLOv8n garbage model in Colab | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-04-25 | 2026-04-10 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
qkrvcBXPtUyxsqg_4JtxVskADLVJ | Implement MongoDB logging and pose-based intent (v1) | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-06-15 | 2026-05-15 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
GsRAYHcUbEeKYPjbWri5o8kAJ9QQ | Redesign for live camera with object tracking (v2) | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-10-08 | 2026-10-01 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
DaU1ZZsuxEuYI7EVDGIyqMkAIHkU | Implement throw vs accidental intent rules (v2) | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-10-10 | 2026-10-05 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
ohCFx7AkAE6aEMAsvpHwsMkAItK3 | Implement sinking-garbage and pool-floor detection | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-10-12 | 2026-10-07 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
XDoyU_DiQEaIZIveXuiN1skAA8Li | Record throw clips and retrain model (v2 notebook) | E854ocLHuUqfNhqRP--Xr8kAGJvf |  | Not started | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-10-22 | 2026-10-14 |  | false
uruv5qv470qtHFN741gqMskAEKdX | Integration testing (27 automated system checks) | 3YDvbezNLkS6nD8ub3n1LMkAJ87h |  | Completed | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-09-05 | 2026-08-15 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
aXhFiPPYskG89GPspoFYwckAOOLD | Integrate water card into dashboard and test sensors | 3YDvbezNLkS6nD8ub3n1LMkAJ87h |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-09-05 | 2026-08-15 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411
d89TgB5ODUqw4mfUhfs7TckAKhrB | Integrate drowning module into dashboard and test | 3YDvbezNLkS6nD8ub3n1LMkAJ87h |  | Completed | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-08-15 | 2026-07-20 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
aASwIWEJXkSJjJtCuwDeX8kAOZSg | Integrate garbage module into unified dashboard | 3YDvbezNLkS6nD8ub3n1LMkAJ87h |  | Completed | Medium | 7d4d2156-a035-4149-9b74-1569eec88cfa | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-07-20 | 2026-07-01 |  | false | 2026-10-14 | 85db442f-de47-4636-be09-222165aeebbd
3LM-IhnmZ0-3SJ4hrQZc7MkANjab | Write individual and group final thesis | uFnhTM6lSkW0gg4PVuEVgckAK_OA |  | Not started | Medium | 85db442f-de47-4636-be09-222165aeebbd | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-10-22 | 2026-09-25 |  | false
EIAe8TJQ8ESdomsZzcVH4ckAKmRg | Write individual final thesis (Component 2) | uFnhTM6lSkW0gg4PVuEVgckAK_OA |  | Completed | Medium | 5e525bf1-841d-402e-859b-015249e8b411 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-10-20 | 2026-09-25 |  | false | 2026-10-14 | 5e525bf1-841d-402e-859b-015249e8b411
ArWdWDhaFE-d9vlCtzFkl8kAC1LT | Write individual final thesis (Component 3) | uFnhTM6lSkW0gg4PVuEVgckAK_OA |  | Not started | Medium | 3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | 85db442f-de47-4636-be09-222165aeebbd | 2026-10-14 | 2026-10-20 | 2026-09-25 |  | false

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
ONxyLl54k0mTc_lJ2n9c_8kAPr_3 | Planning
b-So2S7d70yp2V2sRjkJkMkAHhOk | Research
E854ocLHuUqfNhqRP--Xr8kAGJvf | Development
3YDvbezNLkS6nD8ub3n1LMkAJ87h | Testing & Integration
uFnhTM6lSkW0gg4PVuEVgckAK_OA | Documentation

## Users
User ID | User Name | Email
85db442f-de47-4636-be09-222165aeebbd | SAAJITH M H M it22156310 | it22156310@my.sliit.lk
3c39550c-1cbf-4066-b45f-7ea0b43a1c13 | SHAFAN N M it22248480 | it22248480@my.sliit.lk
5e525bf1-841d-402e-859b-015249e8b411 | NILOGINI Y it22247254 | it22247254@my.sliit.lk
7d4d2156-a035-4149-9b74-1569eec88cfa | ARSALAN M. Y.S. it22277336 | it22277336@my.sliit.lk